## Slide 1: GIB Retail Performance Testing
3rd March’2020

## Slide 2
Agenda
Performance Testing Process
Performance Testing Approach
Performance Testing Solution - GIB Retail
Project Timeline
Sprint Wise User Stories and Deliverables
Performance Testing Tool Comparison
Project Team Structure
Challenges & Assumptions
Key Action Points

## Slide 3
Performance Testing Solution - GIB Retail
Performance Testing Objective
Baseline & Benchmarking
Load handling capacity of Target Systems and channels
Breakpoint of Target systems and Channels
Measure Response Time
Performance Analysis
End to End Simulation
Core &
Flexible team
Standard performance test approach
Performance Testing Tools
Governance
Design accelerators & design
Automated Collection of performance metrics & Analysis
Realtime scenario simulation
VBL
UBS
IB
MB
Cortex
AFS
Performance Testing Factors
Load and Volume
Breakpoint/Stress
Endurance
Performance Testing Tool
Jmeter - Open source
Channels & Target Systems
Other Retail Back End Systems
System Integrator
CRM

## Slide 4
Performance Testing Approach
Kony MF & VBL
Middleware/SI
Server
DB
Retail Back End Systems
Web
App
DB
IB
MB
HTTPS
End to End Simulation (Channels)
IB: Internet Banking
MB: Mobile Banking
Recommended Testing Types
Load/Volume Testing
Stress Testing
Endurance Testing
Reporting & Analysis
DB logs & Reports
Core Web/App server logs
Middleware logs
External
Users
Server
DB
Web
Services
Web
Services
Performance Testing Tool
Other Retail Interface
Web
App
DB

## Slide 5
Performance Testing Process
REQUIREMENT GATHERING & PLANNING
DESIGN
EXECUTION
CLOSURE
  Script development
  Script enhancements
  Identify Test data requirement
  Test data setup and creation
  Test environment readiness
  Script and environment health check
  Test execution in profiling approach
  Monitor execution
  Collate test results
  Analyze test results
  Execution summary report
  Test results consolidation
  Final Performance Test report preparation & presentation
  Define scope & objective
  NFR gathering & understanding
  Tool compatibility check
  Application walkthrough
  Technical architecture
  Finalize Transaction scope
  Environment analysis
  Define work load model
  Risk analysis & mitigation
  Publish Test plan
Test Plan
Scripts
Execution Summary Report
Test Report
Major Deliverables
  Bottleneck isolation & identification
  Root cause analysis
  Tuning Recommendations
ENGINEERING
Engineering phase is excluded as part of phase 1

## Slide 6
Tentative Project Timeline and Cost
  Note:
  The above provided timeline & cost are tentative and derived based on below scope:
    Internet Banking - 6 Transactions(Max.)
    Mobile Banking - 6 Transactions(Max.)
  Scope of work shall be revisited and finalized during planning phase
  Timeline does not included Turn Around Time for defect fixes. In case of stakeholders agrees to fix performance defects raised as part of execution phase, timeline and effort would be revisited accordingly
  Cost specified is indicative and it is excluding tool cost
Phase | M1 |  |  |  |  | M2 |  |  |  | Total Weeks | Total Cost
 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 |  | 
Sprint 1 | 2 |  |  |  |  |  |  |  |  | 9 | $40,156
Planning | 1 |  |  |  |  |  |  |  |  |  | 
Design & Execution |  | 1 |  |  |  |  |  |  |  |  | 
Sprint 2 |  |  | 2 |  |  |  |  |  |  |  | 
Planning |  |  | 1 |  |  |  |  |  |  |  | 
Design & Execution |  |  |  | 1 |  |  |  |  |  |  | 
Sprint 3 |  |  |  |  | 2 |  |  |  |  |  | 
Design |  |  |  |  | 1 |  |  |  |  |  | 
Execution |  |  |  |  |  | 1 |  |  |  |  | 
Sprint 4 |  |  |  |  |  |  | 3 |  |  |  | 
Execution |  |  |  |  |  |  | 2 |  |  |  | 
Closure |  |  |  |  |  |  |  |  | 1 |  | 

## Slide 7
Sprint 1 & 2
Sprint 1
Gather and Analyse customer usage trend from production
Derive workload model
Sprint 2
Gather technical details/architecture of identified performance test environment and evaluate against production
Prepare and publish Test Plan
Finalize transactions in scope for phase 1 performance testing
Identify and prepare performance test environment
Develop scripts for at least 3 transactions from finalized scope
Conduct sanity and baseline execution for developed scripts
Monitoring tools configuration in identified test environment and access if required
Develop scripts for 5 transactions from IB finalized scope
Conduct 10% and 30% load test based on derived work load model for 8 transactions
Test data creation and maintenance
Test data creation and maintenance
Tools installation and set up
Sprint 1 Key Deliverables
Transactions in scope for MEEM KSA IB and MB
Test environment for Performance Testing
Workload model
Performance scripts for 3 Transactions
Execution summary report for baseline test
Sprint 2 Key Deliverables
Delta report between performance test environment and production for extrapolation
Performance Test Plan
Performance scripts for 5 transactions
Execution summary report for 10% and 30% load test

## Slide 8
Sprint 3 & 4
Sprint 3
Develop scripts for remaining 4 MB transactions in scope
Sprint 4
Conduct stress to identify breakpoint
Script maintenance activity
Conduct 60% and 100% load test with all transactions in scope
Analyse performance and prepare report highlighting performance issues
Test data creation and maintenance
Conduct endurance test
Collate results of all round of execution
Prepare and publish Final Performance Test Closure report
Sprint 3 Key Deliverables
Performance scripts for 4 Transactions
Execution summary report for load test
Performance defects report
Sprint 4 Key Deliverables
Performance script repository with 12 critical transactions from MEEM KSA IB & MB
Execution summary report for stress and endurance test
Final performance test closure report

## Slide 9
Performance Testing Tool Comparison
JMeter
IBM RPT
Load Runner
Non GUI mode execution
Constraints on report generation
Licensed
Cost is less compared to load runner
Cost
  1-500 VUs - $945 / Month
  500-999 VUs - $1260 / Month
  Above 1000 VUs - $1575 / Month
Lack of protocols for legacy systems
Licensed
License costs are high
Cost:
  999 VUs - $ 4995 / Day
  9999 VUs - $ 34996 / Day
Multiple components and hardware requirement is comparatively high
PROS
CONS
Open source
Easy Installation
Supports major web and web services protocol
Can be integrated with CI tools
Support Java, bean shell and Groovy scripting
Implemented in GIB, Metro Bank, Bank ABC and Bank Muscat
Supports multiple protocol
More insights on KPI’s
Customized reporting
Can be integrated with APM tools
Real time execution monitoring
Flexible licensing mode
Implemented in BAB, Riyadh Bank, Bank Muscat, KIB, QIB, ANB, Alawwal, Al Rajhi, etc..
Supports 50+ protocol
Protocols that support legacy systems and other technologies
Real time execution monitoring
Can be integrated with APM tool
Could based load generators
Implemented in SABB and SAMBA

## Slide 10
Project Team Structure
Project Sponsor
IT Management
Project Manger
Wael Alghadban
Support Teams
Testing Team
Infrastructure
Abdullah AlHaddad
ITCC & Staging Team
Fawaz Shamim &
Hassan AlTalib
App/Dev Team
Kony/VBL
Sulaman Riaz/Asif Ishaq
CRM
Abdulhameed AlHassan
UBS
Joseph Yaghlji
Middleware/SI
Baqer Alghatam
Test Lead
Guna
Test Engineer
Vimal
Test Engineer 2
Functional Team
Arunkarthick Thangaraj
Performance Team
Data centre

## Slide 11
Support Required
Teams | Support Required
Infrastructure | Enabling monitoring tools(Dynatrace, SCOM & Oracle Enterprise Monitor) in test environment Provide access to servers(App & DB), monitoring tools in test environment Provide technical details/sizing of test and production environment
ITCC & Staging Team | Provide customer usage data(User base, User logins, transaction volume, etc..) from production to analyze trend
Application (Kony/VBL) | Application readiness in test environment Providing mobile application build to install in emulator Disabling OTP/Encryption in there are any Support in providing required test data Pre & post execution support in terms of application setup, logs, etc. Performance Tuning/Defect fixes if any in case of critical/showstopper issue
SI & B2B | Stub configuration for external systems/gateways if required Pre & post execution support in terms of application setup, logs if required
UBS | Provide valid required test data(CIF’s, active account numbers with sufficient balance) Provide application logs post execution if required
Datacentre | Execute EOD jobs and provide jobs elapse / logs for analysis if any
Functional Team | Application walkthrough Functional support if required

## Slide 12
Challenges & Assumptions
  Performance Testing of Kony platform and ATM were not performed earlier
  Production similar environment is required to conduct benchmarking activity
  In case of any show stopper defects(Infra/App due to performance ) in between the execution, load and volume achieved till that point will be considered as break point.
  Performance benchmarking exercise will encounter challenge if any critical/showstopper performance defects are identified during execution phase
  In case if any of the performance defects raised during execution are agreed for fixes by stakeholders, we need to reiterate the test to validate provided fixes and proceed further. This might affect overall planned timeline and efforts.

## Slide 13
Key Action Points
S. No | Key Action Points | Assigned To | Status | Comment
1 | Gather customer usage trend (Logins and Transaction volume ) from production for past 6 months | Reporting Team | Pending | 
2 | Analyze gather information form production to understand usage trend and identify scope | PT Team | Open | Dependent on action point one
3 | Finalize application and transaction scope | - | Open | 
4 | Identification and preparation of environment dedicated for Performance Testing | - | Open | 
5 | Workstation allocation and tools installation | - | Open |